This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a re
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that fe
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the a
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that fe
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the a
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that fe
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the a
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
Select Feature ID from Product Backlog - The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that fe
Select Feature ID from Product Backlog - Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the a
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
## Product_Backlog
Product Name:	JADE Manager					Complete Fields in Green!!!
Team ID:					Features Remaining at end of Sprint / Sprints

	Team Member Name					Initials	Student ID
Required	Nikita Ashok Menon					NAM`	1001548454

Sprint #	Remaining	Completed This Sprint			Comment
0	33			Total	Total number of features (in column H)
1	29	4		1	Total features left at the end of Sprint #1
2	26	3		2	Total features left at the end of Sprint #2
3	26	0		3	...and so on
4	26	0

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new coffee flavor	Stock and sell coffee products
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new donut	Stock and sell donuts
GUI	3	1	8	1	Finished in Sprint 1	Manager	Use a main window (GUI) with minimal menu bar only	Reduce training costs	This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
PS	4	1	5	1	Finished in Sprint 1	Customer	List the coffee and donut products in a dialog	See what is available (and later, see what the Customer can order)	This is effectively a string stream to a dialog with an OK button
IGUI	5	2	13	2	Finished in Sprint 2	Manager	Use dialogs to create new coffee and donut products	Reduce training costs	One dialog each for coffee and for donuts
BB	6	2	3	2	Finished in Sprint 2	Server	Use a button bar in the main window for common actions	Access features more quickly
CB	7	2	2	2	Finished in Sprint 2	Server	Create a new beloved customer	Keep track of our customers
CO	8	2	8	3	In Work	Server	Create an order of multiple products	Serve everyone in a customer party
POC	9	2	3			Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB	10	3	8			Customer	Associate the order with a customer	Self-order and not have to deal with people	“What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CE	11	3	13			Manager	Create a store that stocks items and maintains a cash register	Manage the emporium	This includes item stocks, server and customer lists, and the cash register
MST	12	4	5			Manager	Manage the state of each order (unfilled -> filled and unpaid -> paid,, or unfilled / unpaid -> canceled)	Ensure each order is filled and payment collected
SAVD	13	4	8			Manager	Save all data to a default file on exit or command	Ensure our data isn’t lost
LOAD	14	4	5			Manager	Load data from a default file on startup	Ensure our data isn’t lost
POS	15		5			Server	Show the products in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX	16		21			Customer	Add and display pictures for each item	Better understand the menu
CM	17		3			Owner	Create a new manager	Delegate management tasks to a pro
P&L	18		8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy
RI	19		5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers
RTM	20		8			Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members
AI	21		8			Server	Restock donuts and coffees	Ensure we can fill every order
RO	22		8			Manager	Create an Order Report, showing all pending orders (unfilled and filled but unpaid)	Better manage our production process
RB	23		5			Manager	Display a Customer Report, listing all info about each customer	Better attract repeat customers and handle complaints
EF	24		8			Manager	Edit a product	Improve our data and keep it synced to reality
ROA	25		3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
SALL	26		5			Owner	Save all data to a specified file	Franchise my company
LALL	27		5			Owner	Load data from a specified file	Franchise my company
CENEW	28		13			Owner	Create a new franchise	Franchise my company
XI	29		21			Manager	Retire a product (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
CS	30					Manager	Hire a NAMED server, and login by server name	Keep track of our employees
ASTO	31					Manager	Also associate a server with the order they fill	Keep track of our employee productivity
XT	32		13			Manager	Suspend a server (no longer allow their selection for an order	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	33		5			Manager	Restore a server	Add a former team member tack into service

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 30		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 06		Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	3	1
Day 2 Left	2	1
Day 3 Left	1	1
Day 4 Left	0	1
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CF		Stock and sell coffee products	Completed Day 1
2	CC		Stock and sell donuts	Completed Day 2
3	GUI		Reduce training costs	Completed Day 3
4	PS		See what is available (and later, see what the Customer can order)	Completed Day 4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Nov 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 13		Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	2	1
Day 2 Left	1	1
Day 3 Left	0	1
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	IGUI		Use dialogs to create new coffee and donut products	Completed Day 1
2	BB		Use a button bar in the main window for common actions	Completed Day 2
3	CB		Create a new beloved customer	Completed Day 3
4	CO
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_03_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 20		Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint_04_Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 27		Tasks / Days
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84